## Frontend Technical
Table 1
Sr No | Area | Technical Question | Best Practise Proposal | Link | Yesly Comments | Status | Board ref | Changed since 26 Sep 2026
FE-01 | App Framework | Can you confirm the final React Native and Expo versions we should use for the first development release? | Use the agreed Expo SDK and React Native versions and lock them before development starts. | Expo Documentation · React Native | to be verified: the exact Expo SDK and React Native versions, pinned by Spinach before development starts and stated in the project plan. The two supplementary sheets give two different floors (0.76+ on Foundation row 2, 0.87+ on row 3); one pair of numbers, please. HoA confirms on receipt. | owed - to be verified: the exact Expo SDK and React Native versions, pinned by Spinach before development starts and stated in the project plan | W36
FE-02 | Development Setup | Do you want us to use the Expo managed workflow only, or should we allow native configuration/custom development builds where required by third-party integrations? | Start with Expo. If a third-party SDK requires native configuration, use Expo Development Builds rather than limiting the project to Expo Go. | Expo Development Builds | Accepted as proposed. Expo with Development Builds from day one; Razorpay, Finvu and biometrics need native configuration; Expo Go is not a constraint. | frozen | I01, I09
FE-03 | TypeScript | Can we use TypeScript across the complete mobile application? | Yes. Use TypeScript for screens, components, hooks, state, navigation and application models. | TypeScript | Accepted as proposed. | frozen
FE-04 | Navigation | Can you confirm that the app will use one navigation approach throughout the application? | Use Expo Router as the single navigation layer. Avoid mixing multiple navigation patterns unless there is a specific technical requirement. | Expo Router | Accepted as proposed. Expo Router only, one route per screen ID (A02, D02a, K05), so a screen ID, a route and an event name read the same. | frozen
FE-05 | Navigation Structure | How should we separate the public, onboarding and authenticated sections of the application? | Use route groups for public, onboarding and authenticated areas so access rules remain centralised. | Expo Router — Authentication | Three route groups, drawn by the board's paywall line. Public: A01, A02, A03. Registered and unpaid: A04, R01 to R12, X01, P01 to P05. Paid: O01 onward (A05 to A10c, D, G, K, E, H, Q). The tier (DIY, DIWM, DIFM) is read from the subscription state, never from a route. The full map is Part E. | frozen | N01, P05
FE-06 | Authentication Screens | Which screens should be accessible before login and which should only be available after authentication? | Define the route-access map before implementation so authentication rules are not implemented separately inside individual screens. | Expo Router — Authentication | The map in Part E. Access is decided by the server-side state router (N01, states S1 to S25), never by a check inside a screen; a screen reached out of state redirects to that state's landing screen. | frozen | N01
FE-07 | Session Expiry | What should the user see if their session expires while they are using the application? | Handle session expiry centrally and take the user through the agreed re-authentication flow without leaving the application in an inconsistent state. | Expo Router — Authentication | After 30 minutes of inactivity the session locks. Re-authentication is biometric if enrolled, otherwise OTP (A02 with the number prefilled, then A03). After re-auth the person lands on the exact screen they left (minutes 16 Sep 2026, item 4). Nothing is lost: every saved step is on the server. There is no password and no PIN in this app. | frozen | A02, A03
FE-08 | Deep Links | Will emails, SMS, notifications or third-party services need to open a particular screen inside the application? | Define the required deep-link paths before development. Do not put sensitive information directly into URLs. | Expo Linking | Yes. Every returning-user state S1 to S25 carries a deep_link on the states tab (N01): that is the screen a push, a WhatsApp message or an email opens. One route per screen ID. No personal data in any URL: a signed token resolves to the person on the server. to be verified: the universal-link domain (W35). | frozen | N01, W35
FE-09 | App Re-entry | If the user leaves the application during payment, KYC, Account Aggregator or another external flow, where should they return when they come back? | Each external journey should have a defined resume/recovery screen and state. | Expo Linking | Every external flow has a return state on the board. Payment: S2c lands on P04; a failed renewal lands on Q03b (S12). eSign: S2b lands on P03. AA consent: the return from the vendor lands on D01 with the fetch running in the background; a decline or a timeout lands on A09. CAS: S17 lands on A10a, then A10b. A la carte payment (K04): K05. On every return the app re-checks the vendor's authoritative status before it shows success. | frozen | N01, P03, P04, A06, A09, A10a, K04
FE-10 | Android Back | Are there any screens where the Android back button should behave differently from normal navigation? | Define back behaviour for forms, multi-step journeys, bottom sheets, confirmation screens and external flows. | React Native BackHandler | By template, Part D. In short: on the reveal and the spine, back is the previous question with the value kept; in a vendor webview (A06, P03, P04) back cancels the vendor step and lands on the state's landing screen; on a progress screen (R08, A07, G01, G01a) back is disabled; on a sheet back closes it; on a hub (O02, H01) back minimises the app; on P01 back is X01. | frozen | Part D
FE-11 | State Management | Which frontend state management approach should we use for shared application state? | Use Redux Toolkit for shared application/client state. Keep the store modular and organise state into feature-based slices. | Redux Toolkit · Redux Toolkit + TypeScript | Accepted as proposed. Redux Toolkit with one feature slice per board section: reveal (R), checkout (P), source (A05 to A10c), spine (D), plan (G), calls (K), execution (E), home (H), subscription (Q). | frozen
FE-12 | Redux Scope | Which information should be stored in Redux and which information should remain local to a screen/component? | Use Redux for genuinely shared application state. Keep temporary UI state and screen-specific state local where possible. | Redux Toolkit | Shared: session, subscription and tier, the current state (S number), spine completion flags and progress, aa_status, the offline write queue. Local: a screen's own inputs until autosaved, sheet open or closed, scroll. Server data lives in TanStack Query and is never copied into Redux. | frozen | O02
FE-13 | Server State | How should API data, caching and refetching be handled in the mobile application? | Use TanStack Query for server/API state. Redux should not be used as the API cache. | TanStack Query — React Native | Accepted as proposed. | frozen
FE-14 | State Persistence | Which application information needs to remain available after closing and reopening the app? | Persist only the state that is actually required. Sensitive information should use secure device storage. | Expo SecureStore | Persist: the last route, the session tokens (secure storage), the biometric flag, the encrypted queue of spine values not yet synced (purged on sync). Nothing else. The server holds every saved step (minutes item 4). No persisted query cache. | frozen
FE-15 | Feature Structure | Can we organise the frontend by feature/user journey instead of keeping all screens and components in common folders? | Use a feature/domain-based structure. Each feature can own its screens, components, hooks and state/query logic. | Redux Toolkit — TypeScript | Accepted as proposed; folder names follow the board's section letters (FE-11). | frozen
FE-16 | Component Structure | Which UI components should be reusable throughout the application? | Create a shared component layer for buttons, inputs, cards, headers, bottom sheets, dialogs, loaders, alerts and repeated financial UI patterns. | React Native Components | The 21 templates on the board are the shared component list: T-tap, T-num, T-sheet, T-progress, T-chart, T-hub, T-card, T-card-stack, T-list, T-detail, T-review, T-webview, T-paywall, T-source, T-upload, T-picker, T-locked, T-split, T-video, T-table, T-msg. A screen is an instance of its template with its fields. Build one component per template; buttons, inputs, headers and loaders sit underneath. | frozen | X00
FE-17 | Design System | Can you confirm which Figma file/version will be treated as the final source of truth for the mobile UI? | Use the approved Figma design as the source of truth and convert agreed typography, colour, spacing and component rules into reusable frontend tokens. | React Native Components | to be verified: there is no Figma yet. Spinach owns visual design and produces it after the frozen wireframes. Until an approved visual design exists, Wireframes v0.2 on the board is the source of truth for structure, fields, tags, states and events. The Figma file and its version are recorded on X00 when they exist. | owed - to be verified: there is no Figma yet | X00, W22
FE-18 | Design Changes | How should we handle UI changes made in Figma after development has started? | Any design change should be reviewed for frontend impact before implementation. The approved design should remain the source of truth for visual QA. | React Native | A change to a frozen screen's template, fields and tags, branches, states or events goes through the unfreeze log (date, screen, cause, what changed). A visual-only change (colour, type, spacing, motion) does not, and the approved design is the visual QA source. Copy, prices, counts, bands and grid values are config and never a code change (I15). | frozen | X00, I15
FE-19 | Styling | Can we use NativeWind as the standard styling approach for the application? | Use NativeWind with shared design tokens and reusable components rather than screen-specific styling wherever possible. | NativeWind | Accepted as proposed. | frozen
FE-20 | Responsive Behaviour | What device sizes should the mobile application support? Do we need tablets or foldable devices? | Confirm the supported device matrix before development. Avoid relying on fixed screen dimensions. | React Native Dimensions | Phones only. No tablets, no foldables. iOS 16+ and Android 10 (API 29)+ as proposed on the Foundation sheet. Layouts reflow; no fixed dimensions. | frozen
FE-21 | Orientation | Should the application support portrait only, or should landscape orientation also be supported? | Use portrait by default unless the product specifically requires landscape. Any exceptions should be identified before implementation. | Expo Screen Orientation | Portrait only, the T-chart screens included. | frozen
FE-22 | iOS / Android Differences | Are there any flows where iOS and Android should intentionally behave differently? | Keep behaviour consistent wherever possible, while allowing platform-specific implementation where required by the OS. | React Native — Platform-Specific Code | None intended. The one platform difference is SMS auto-read of the OTP on Android (A03). No Google or Apple sign-in in V1 (I22, later). | frozen | A03, I22
FE-23 | Forms | What are the rules for mandatory, optional and conditionally displayed fields in each form? | Use React Hook Form for complex forms and agree on field behaviour before implementation. | React Hook Form | Already on the board since 17 Sep 2026: every input screen carries a "Moving forward" block and every field a tag (required, optional, default, system, read); 79 screens, 158 fields. Conditional fields are written on their screen: the P02 address only when the KRA record is not found; the K05 same-adviser chip only when the continuity flag is on; a D screen opens only for a type ticked on D02, D03 or D04. React Hook Form accepted. | frozen | Wireframes v0.2
FE-24 | Form Validation | Should validation happen while entering information, on blur, or only when the user submits the form? | Agree on a consistent validation pattern. Client-side validation should provide immediate feedback where useful. | React Hook Form | One-question screens (T-tap, T-num): validate on Continue, with the format mask live (digits, Rs grouping). Multi-field forms (P02, D01a, D03a, D04a to D04c, D07a): on blur per field and again on Continue. Never on every keystroke. | frozen | Part D
FE-25 | Validation Library | Can we use Zod for frontend validation schemas? | Use Zod for reusable validation schemas, especially for larger and multi-step forms. | Zod | Accepted as proposed. | frozen
FE-26 | Validation Messages | Can you provide or confirm the final wording for validation and user-facing error messages? | Keep messages short and clear, and tell the user what needs to be corrected. | React Hook Form | The copy is the content track (owner: Copy) and lands by screen ID and copy slot without a release (I15); build with placeholder text. Rule for the placeholders: short, says what to fix, no technical words. to be verified: the validation and error copy (W39). | frozen | I15, W39
FE-27 | Input Rules | What are the exact rules for amounts, decimal values, phone numbers, names, allowed characters and maximum lengths? | Confirm these rules before creating reusable input components so the same behaviour is followed throughout the application. | React Native TextInput | Amounts: whole rupees, no decimals, Indian grouping (12,50,000), "L" and "Cr" shorthand accepted on entry and expanded, 12 digits maximum. Mobile: +91 only at launch, 10 digits, first digit 6 to 9. OTP: 6 digits. PAN: 5 letters, 4 digits, 1 letter, the fourth letter P. Name: as per PAN; letters, spaces and dots; 100 characters. Date of birth: 18 or older. Percentages: whole numbers. The per-field bands and validation ranges come as one table and do not block the components: to be verified: the bands and ranges table (W40). | frozen | A02, A03, P02, W40
FE-28 | Keyboard Behaviour | Are there forms where the keyboard should automatically move between fields or where the screen should scroll when the keyboard opens? | Use keyboard-aware layouts for long forms and define the expected behaviour for each major form journey. | React Native KeyboardAvoidingView | Numeric keypad on every T-num screen with the keyboard's Done acting as Continue. Keyboard-aware scrolling on the multi-field forms (P02, D01a, D03a, D04a to D04c, D07a). Auto-advance across the six OTP boxes on A03 only. No auto-advance anywhere else: one question per screen. | frozen | Part D
FE-29 | Loading States | What should users see while a screen or action is loading? | Every API-driven screen should have a clear loading, disabled or progress state. | TanStack Query | By template, Part D. Long operations have their own progress screen on the board: R08 (sketching your paths), A07 (fetching), G01 and G01a (building your plan). Every API-driven screen shows a skeleton, never a spinner over content. Navigation on the spine is optimistic: the autosave is queued and retried; a write that still fails shows a non-blocking "not saved yet" line and the next Continue waits for the queue to drain. | frozen | R08, A07, G01
FE-30 | Empty States | What should be displayed when the user does not have any data yet? | Create reusable empty-state patterns rather than designing each empty screen differently. | React Native Components | Accepted as proposed. The empty states are already named per screen on the board (K06 no calls yet, H06 empty vault, G12 no holdings, D01 no members yet, H04 nothing queued); their copy is the content track. | frozen
FE-31 | Error States | What should the user see for validation errors, network failures, expired sessions and failed third-party operations? | Define separate UI states for each failure type so users understand what action they need to take. | TanStack Query — React Native | Validation: inline, next to the field. Network: the offline banner plus the queued write (Connectivity row 3). Expired session: FE-07. Failed third party: a drawn state per vendor: A09 (AA partial or failed), A05a (bank slow), A10c (parse failed), P03 (eSign retry, S2b), P04 (payment failed) and Q03b (renewal failed, S12), the E screens per vendor status. Each says what to do next. | frozen | A09, A05a, A10c, P03, P04, Q03b
FE-32 | Retry Behaviour | Which actions can users safely retry? | Allow retry for recoverable operations. Do not blindly repeat sensitive financial or transactional actions. | TanStack Query — Retry | Accepted as proposed. Retry freely: reads and autosave writes. Never blind-retry a payment (P04, K04), a consent (A06), an eSign (P03), an order or a mandate (E03, E04, E10, E11): re-query the vendor by reference first. | frozen
FE-33 | Drafts | Which forms or journeys should allow users to save and continue later? | Identify all draft-enabled journeys before development. Keep the draft experience consistent across the application. | Redux Toolkit | Every reveal screen (R01 to R07) and every spine screen (section D) autosaves per field (rule 12). The reveal resumes at the first unanswered screen (S1); the spine resumes from O02 at the first incomplete screen (S4); checkout and vendor flows resume by state (S2b, S2c, S17). K01's topic and note are the only other draft. Nothing else. | frozen | N01, O02
FE-34 | Unsaved Changes | What should happen if the user leaves a form before completing it? | Warn the user before losing meaningful information and restore the draft where the journey supports it. | Expo Router | No unsaved-changes dialog anywhere. Leaving a screen is a silent autosave with a Saved toast (rule 12; Vatsal, 11 Sep 2026); the "when will you finish" prompt was considered and rejected. One exception, and it is a line on the screen, not a modal: a vendor webview (A06, P03, P04) says that leaving restarts the vendor step. This overrides the proposal. | frozen | D spine, A06, P03, P04
FE-35 | Multi-step Forms | Which journeys are multi-step flows, and can users move backwards and forwards between steps? | Use a consistent multi-step pattern with clear progress and state preservation. | React Hook Form | Multi-step flows: the reveal R01 to R07 (back and forward, values kept); the spine D01 to D10 in eight sections, with the section map and the endowed progress ring on O02 (rule 11) and a relief card between sections (D12a to D12h); the RPQ D08a to D08h (tap only, back allowed, a changed answer re-scores D09); checkout P01 to P05 (forward only past P03: a signed agreement is not signed again while its version is current); the one-time investing setup E02. | frozen | O02, D12a, D09, P03, E02
FE-36 | App Backgrounding | What should happen if the user puts the app in the background in the middle of a form or transaction? | Preserve recoverable UI state and re-check the relevant transaction state when the application becomes active again. | React Native AppState | Accepted as proposed. On return to the foreground re-check payment (P04), eSign (P03) and consent (A06, A07) with the vendor before showing any result. | frozen
FE-37 | App Restart | What should happen if the application is completely closed while the user is in the middle of a journey? | Recover the last valid state where the journey supports recovery rather than assuming the previous screen is still active. | Redux Toolkit · Expo SecureStore | Read the device's last route and the server's state; when they disagree the server wins and the state router lands the person (N01). Every saved step is on the server (minutes item 4), so a restart never loses data. | frozen | N01
FE-38 | Account Aggregator | How will users move between the YESLY app and the Account Aggregator flow? Is it a native SDK, browser flow, app-to-app flow or deep link? | Confirm the exact journey and integration method before implementation. Keep provider-specific implementation isolated from the rest of the application. | Expo Linking | The flow is drawn: A05 chooses; A06 is Finvu's consent flow in a webview; the return lands on D01 and the fetch runs server-side in the background while the person answers (a "fetching your accounts" pill opens A07); A08 opens as a sheet when the fetch completes; A09 on a decline, a timeout or a failure. Provider-specific code stays behind one module, as proposed. to be verified: whether Finvu's current integration is a redirect URL, a hosted webview or a React Native SDK, read from the Finvu documentation Spinach already holds (W37). | frozen | A05, A06, A07, A08, A09, I01, W37
FE-39 | Account Aggregator States | What should users see for consent pending, successful connection, cancellation, timeout and partial/failed data retrieval? | Define each state separately rather than treating the entire Account Aggregator process as a simple success/failure screen. | React Native AppState | Each state is drawn. Pending: the pill on the section strip (A07 on tap). Connected: A08, the sheet, with include and exclude per account. Cancelled, declined or timed out: A09 with the CAS and manual ways. Partial: A09 rows per FIP with retry; "continue with what we have" lands on D01. A later retry that succeeds merges into A08 with a notification. Bank slow: A05a. | frozen | A05a, A07, A08, A09
FE-40 | Payment UI | What payment states should be shown to users? | At minimum, define initiated, processing, successful, failed, cancelled and recovery states. | Razorpay Documentation | Initiated and processing: P04 in progress. Success: P05. Failed: P04 "payment failed, retry with another method, nothing is lost". Abandoned after the eSign: S2c (lands on P04; the agreement is not signed again). Mandate pending bank approval: P04 allows entry with billing marked pending. Recovery: re-query Razorpay by order ID before any retry. Renewal failed: Q03b and H01f (S12). Lapsed: Q03c and H01g (S13). Refund requested: Q03a (S24). | frozen | P04, P05, Q03a, Q03b, Q03c, N01
FE-41 | Payment Re-entry | If the user closes the app during payment, how should they resume or check the result? | The UI should support payment recovery when the user returns instead of assuming that closing the app means the payment failed. | Razorpay Documentation | State S2c. On return the app asks the backend, which asks Razorpay by order and payment ID; the webhook is authoritative; closing the app is never read as a failure. | frozen | P04, I09
FE-42 | KYC / eSign | Which KYC/eSign screens are handled inside YESLY and which are handled by a third-party provider? | Confirm the exact user journey, hand-off mechanism and return flow before implementing the screens. | Client/provider documentation to be confirmed | P02 is in the app: name as per PAN, PAN, date of birth, email; the KRA lookup is server-side; the address fields appear only when the record is not found. P03 is the vendor eSign inside a webview; the return lands on P04. Full KYC for execution (bank, nominee, FATCA) is deferred to E02. The KYC vendor (I06) and the eSign vendor (I07) are open on the Integrations tab (W34, owner Admin with Compliance); the screens do not wait for them. | frozen | P02, P03, E02, I06, I07, W34
FE-43 | KYC / eSign Recovery | What should happen if the user leaves the application during KYC/eSign or the external flow fails? | Provide a clear resume, retry or recovery experience based on the selected provider's flow. | Client/provider documentation to be confirmed | eSign cancelled or timed out: S2b lands on P03 with retry; the existing eSign status is checked before a new request, as proposed. KRA record not found: the address fields on P02; the agreement proceeds. KRA name or date mismatch: inline error, correct and retry. KRA service unavailable: the same path as not found (ask the address), the record is flagged for a later re-check, the agreement proceeds. | frozen | P02, P03, N01
FE-44 | Documents | What document types can users upload, and what are the allowed file size, format and image-quality limits? | Validate basic file requirements before upload and show clear feedback when a file is not acceptable. | Expo DocumentPicker | V1 uploads are the CAS PDF only (A10b): one PDF, password-protected (a depository CAS with the PAN, a registrar CAS with the password chosen at request; A10b asks for it), 10 MB maximum. The vault (H06) is open and takes no uploads in V1. | frozen | A10b, H06
FE-45 | Upload Progress | Should users be able to cancel and retry document uploads? | Show upload progress where practical and provide retry behaviour for failed uploads. | Expo FileSystem | Accepted as proposed. | frozen
FE-46 | Camera / Gallery | Which journeys require camera, gallery or document access? | Request permissions only when the user reaches the relevant feature rather than requesting every permission at first launch. | Expo Camera · Expo ImagePicker | No journey needs the camera, the gallery or contacts in V1; the document picker only (A10b). None of those permissions is requested. | frozen | A10b
FE-47 | Notifications | Which notification types will be sent to users, and which screens should open when a notification is tapped? | Create a notification-to-screen mapping before implementing push notifications. | Expo Notifications | The ladders on the board: N02 (paid, before the plan) and N03 (post-plan) list every push with its state and timing; N04 holds the templates; each state's deep_link on N01 is the screen a tap opens; FCM (I12). | frozen | N01, N02, N03, N04, I12
FE-48 | Notification Navigation | What should happen if the user taps a notification while logged out or while the app is already open? | Notification handling should respect authentication state and route users to the correct destination. | Expo Notifications · Expo Router | Logged out: the tap opens A02 with the number prefilled, then A03, then the state router lands on the deep_link. App open: navigate directly. In both cases the router validates the state first; a stale link lands on the state's current screen, as proposed. | frozen | N01
FE-49 | Accessibility | Are there any accessibility requirements we need to meet for the first release? | Support screen readers, accessible labels, logical focus order and accessible controls. Test with VoiceOver and TalkBack. | React Native Accessibility | Accepted as proposed. Test VoiceOver and TalkBack on the reveal, the spine and checkout. | frozen
FE-50 | Font Scaling | Should the application support the user's device font-size/accessibility settings? | Support system font scaling where practical without breaking important layouts or financial information. | React Native Text | Supported. A number never truncates or wraps into ambiguity; layouts reflow; test at the largest system size. | frozen
FE-51 | Touch Targets | Can we follow accessible touch-target sizing throughout the application? | Yes. Interactive controls should have sufficiently large touch areas and should not depend on small icons alone. | React Native Accessibility | Accepted as proposed. | frozen
FE-52 | Animations | Are there any specific animations or transitions required by the approved designs? | Keep animations purposeful and lightweight. Avoid animations that block important actions. | React Native Animated | None beyond the progress screens (R08, A07, G01, G01a), the reveal chart drawing itself on R09 and the progress ring on O02. Nothing animates in the way of an action. | frozen | R08, R09, O02
FE-53 | Bottom Sheets | Which screens require bottom sheets, action sheets or modal interactions? | Standardise bottom-sheet behaviour, including opening, closing, Android back behaviour and accessibility. | React Native Modal | Sheets (T-sheet): A08, O03, D11a, D11b, D11c. Explainers open in place (A02 "why mobile and not email"). The relief cards D12a to D12h are full screens. Back and swipe close a sheet; standardised as proposed. | frozen | Part D
FE-54 | Charts | Which financial/analytical screens require charts, and what chart types are expected? | Confirm chart types and expected data behaviour before selecting a charting library. Accessibility and large datasets should also be considered. | React Native Accessibility | The T-chart screens: R09 (the two paths: two lines over age), G11 (allocation), H02 (net worth growth, line), H03 (wheel of wealth, radial), H10 (goals progress, bars), H11 (portfolio: allocation plus holdings). Data comes from HoA Core Platform APIs (I04). A chart must render with band (approx) inputs and say so. The library is Spinach's choice. | frozen | R09, G11, H02, H03, H10, H11, I04
FE-55 | Large Lists | Which screens are expected to contain long lists of transactions, investments, documents or other records? | Use virtualised lists such as FlatList and load data incrementally rather than rendering large datasets at once. | React Native FlatList | No list is large in V1 (D01, D07, G14, H04, H06, K06, E08 are tens of rows at most). FlatList is enough; FlashList is not needed. | frozen
FE-56 | Search / Filters | Which lists require search, sorting or filters, and should filter selections remain when users leave and return? | Define filter behaviour per journey and create reusable filter components where the interaction is repeated. | React Native FlatList | None in V1. No search, sort or filter on any list. | frozen
FE-57 | Performance | Are there specific expectations for app launch, screen transitions or large financial datasets? | Define basic frontend performance targets and test important journeys on lower-spec devices as well as development devices. | React Native Performance | Accepted as proposed (Performance sheet row 1). The spine must feel instant: one question per screen, optimistic navigation, the next two screens prefetched. | frozen
FE-58 | Sensitive Screens | Which screens contain financial, payment, KYC, identity or other sensitive information? | Identify these screens early so screenshot behaviour, backgrounding and other platform security considerations can be assessed. | OWASP MASVS | Screenshots blocked (FLAG_SECURE and the iOS equivalent) on A03, A06, A10b, P02, P03, P04, K04, E02, E03, E04, E07 to E11. Allowed everywhere else: people share their plan with a spouse. The app-switcher preview is blurred on every screen that shows a number. | frozen
FE-59 | Local Storage | What information, if any, is expected to remain available locally when the application is reopened? | Keep local storage minimal and avoid storing sensitive information unless there is a clear requirement and secure storage mechanism. | Expo SecureStore | See FE-14: the last route, the tokens, the biometric flag, the encrypted unsynced queue. No plan data, no PII, no persisted query cache. | frozen
FE-60 | Analytics | Which user actions and journeys should be tracked through analytics? | Prepare an agreed event list before implementation. Use one naming and parameter convention throughout the application. | Client-approved analytics provider documentation to be confirmed | The Events tab is the list: 461 events across 194 screens, <screenID>_view on every screen plus the named events (source_choice, gate_met, plan_built, call_booked, return_time_picked, the D-spine set of band, skip and hesitation events); the naming rule is appendix D of plan_v2.md. Tool: Mixpanel (I13, final, Vatsal, 24 Sep 2026); journeys and nudges stay in Zoho Campaigns and Flow, FCM and WATI. | frozen | Events, I13
FE-61 | Analytics Data | Are there any fields or user information that must never be sent to analytics tools? | Do not send sensitive financial, authentication, KYC or personal information unless specifically approved and required. | OWASP MASVS | A payload may carry: screen ID, state ID, event name, band index (never the rupee value), timers, source type (aa, cas, manual, later), tier, a pseudonymous user ID. Never: amounts, PAN, date of birth, name, mobile, email, account numbers, documents. | frozen
FE-62 | Crash Reporting | Which crash/error monitoring platform should be used for the mobile application? | Use the client-approved monitoring platform with application version, release and environment information attached to errors. | Client-approved monitoring provider documentation to be confirmed | Sentry, as proposed on the Analytics sheet, with release, environment and app version attached; no PII in breadcrumbs or tags. | frozen
FE-63 | Frontend Logging | What information can safely be logged during development and production troubleshooting? | Never log passwords, OTPs, authentication tokens, financial identifiers, payment information or KYC documents. | OWASP MASVS | Accepted as proposed. | frozen
FE-64 | Testing | Which user journeys are considered critical and must have automated frontend tests? | Cover important authentication, onboarding, financial, payment, document and recovery journeys with automated tests where practical. | React Native Testing | The critical journeys, each with an automated test: A02 to A03 to the state router; R01 to R09; P01 to P02 to P03 to P04 to P05 with the S2b and S2c returns; A05 to A06 to A08 and to A09; spine autosave and resume (S4); D10 to G01 to G03; K01 to K05 to K02; Q03a and Q03b; E01 to E05 to E06 (V1 without in-app execution, W25). | frozen
FE-65 | Component Testing | Should reusable components have their own component-level tests? | Yes, particularly shared inputs, validation components and other critical reusable UI. | React Native Testing | Accepted as proposed: the 21 template components, the reusable inputs and the validators. | frozen
FE-66 | End-to-End Testing | Which complete user journeys should be covered by E2E testing before release? | Identify critical end-to-end journeys early so test setup can happen alongside development rather than at the end. | React Native Testing | The FE-64 list, with Maestro as proposed on the CI/CD sheet. | frozen
FE-67 | Visual QA | Can we confirm that the approved Figma/wireframe version will be the source of truth for visual QA? | Yes. QA should check typography, spacing, colours, states, interactions and device behaviour against the approved design. | React Native | The approved visual design once it exists (FE-17); until then Wireframes v0.2 for structure, fields, states and events. | frozen
FE-68 | QA Devices | Which physical iOS and Android devices should be included in client acceptance testing? | Define a minimum device matrix covering supported OS versions and common device sizes. | React Native Platform-Specific Code | At least: one Redmi Note class Android on Android 10 and one on the latest Android, one Samsung mid-range, one small-screen iPhone (SE class), one recent iPhone. Spinach proposes the exact matrix. | frozen
FE-69 | Theme | Do we need to support both light and dark system modes, or will the application use a fixed theme? | Confirm the theme requirement before implementation so the design tokens and components are built accordingly. | React Native Appearance | Light only in V1. | frozen
FE-70 | App Permissions | Which permissions should the application request and under what user action should each permission be requested? | Keep permissions contextual and request them only when the related feature is being used. | Expo Permissions | Notifications: asked after P05, at the first reminder or ladder moment (O03 or the first nudge), never at first launch. Biometrics: offered on A03 to a returning user. SMS auto-read on Android through the retriever API (no permission). Files: the document picker on A10b (no permission on current OS versions). No camera, contacts, location or calendar. | frozen | P05, O03, A03, A10b
FE-71 | App Updates | How should users be handled when an older version of the application is no longer supported? | Use a configurable minimum supported app version so outdated versions can be guided to update. | Expo EAS Update | Accepted as proposed. | frozen
FE-72 | Environment Configuration | How should the frontend distinguish development, staging/UAT and production environments? | Keep environment configuration separate and use dedicated EAS build profiles/configuration. | EAS Build | Accepted as proposed. | frozen
FE-73 | Build Configuration | Who will own the Expo/EAS project and production application configuration? | Production ownership should remain with the client, with Spinach receiving the access required for development and release activities. | Expo Application Services | HoA owns the Expo and EAS project, the GitHub organisation, the store accounts and the AWS account; Spinach receives developer and release access, as proposed. The accounts are opened in HoA's legal name now that the registration is in (W35, owner Tech). | frozen | W35
FE-74 | App Identifiers | Can you confirm the final iOS Bundle ID and Android Application ID/package name? | Lock these identifiers before production build configuration. | EAS Build | to be decided: the iOS bundle ID and the Android package name, the reverse of HoA's domain once the domain is confirmed (W35). | open - to be decided: the iOS bundle ID and the Android package name, the reverse of HoA's domain once the domain is confirmed (W35) | W35
FE-75 | App Store Accounts | Can you confirm that the Apple Developer and Google Play Console accounts will be available before production release work starts? | Use client-owned production accounts for the final application release. | Apple Developer · Google Play Console | to be decided: the Apple Developer and Google Play Console accounts in HoA's legal name; the registration is in, so they can be opened now (W35). The financial-app declarations and the listing text follow (W06, Compliance). | open - to be decided: the Apple Developer and Google Play Console accounts in HoA's legal name; the registration is in, so they can be opened now (W35) | W35, W06
FE-76 | OTA Updates | Are we comfortable using OTA updates for compatible JavaScript/UI changes? | Use EAS Update for compatible JS/assets changes. Native changes should continue through a new application build. | EAS Update | Accepted as proposed, with one condition: an OTA update never changes copy on a compliance-flagged screen without the compliance sign-off recorded on the Tracker. | frozen
FE-77 | Release Process | Who will approve the final mobile build before it is submitted to the App Store and Google Play? | Define the approval and sign-off process before the first production submission. | EAS Submit | Product (Vatsal) approves the build; Tech (Gaurav) approves the release infrastructure; Compliance approves the flagged screens' copy. The three sign-offs are recorded on the Tracker before a submission. | frozen
FE-78 | Store Content | Who will provide the final app name, description, screenshots, privacy information and store assets? | Client should provide or approve store content while Spinach supports the technical submission requirements. | Apple App Store Connect · Google Play Console | to be decided: the store listing copy (owner: Copy) and the financial-app declarations (owner: Compliance, W06). Spinach handles the technical submission, as proposed. | open - to be decided: the store listing copy (owner: Copy) and the financial-app declarations (owner: Compliance, W06) | W06
FE-79 | Missing Frontend Requirements | Is there anything in the approved YESLY user journeys or designs that is not covered by this questionnaire? | Review the complete user journey and identify any missing screen, state, interaction or device behaviour before development starts. | Expo Documentation | The board is the requirement: the spec panel on every screen (template, path, fields with tags, logic, continue, states, dev notes, events, compliance flag), the states tab, the Events tab, the Integrations tab. Anything missing is a comment on the screen under the identity Spinach; it lands on the Tracker's question list. | frozen | X00
FE-80 | Frontend Sign-off | Can we consider the frontend requirements ready once all required questions are answered and there are no open frontend blockers? | Yes. Development should start once each required decision is approved, marked N/A or tracked as an agreed dependency. | Expo Documentation | Yes. Every frozen row on the Spinach Questions tab is signed off; every open or owed row has an owner and a date; development starts on the frozen screens and the frozen answers now. | frozen

## React Native Foundation & Archi
Table 1
Sr No | Technical Question | Best Practice Proposal | Official Doc Link | Yesly Comments | Status | Board ref | Changed since 26 Sep 2026
1 | Which React Native framework/toolchain should be used: Expo (managed) or React Native CLI (bare)? | Proposal: Use Expo (managed workflow with prebuild) for faster development, OTA updates via EAS Update, and streamlined native module integration. The React Native documentation now recommends Expo as the default way to create new projects. | React Native – Environment Setup · Expo Docs | Accepted as proposed (see FE-02). | frozen
2 | Which React Native version and New Architecture (Fabric/TurboModules) should be enabled? | Proposal: Target React Native 0.76+ with the New Architecture enabled by default. This includes Fabric renderer, TurboModules, and JSI, delivering faster rendering and more efficient native module loading. | React Native New Architecture | Accepted in principle: the New Architecture on. The exact version is FE-01 (W36). | frozen | W36
3 | What TypeScript configuration should be used? | Proposal: Enable the Strict TypeScript API (default in RN 0.87+). This replaces hand-maintained TS definitions and improves type safety across the codebase. Minimum Node.js 22.13+, Kotlin 2.0+. | React Native Strict TypeScript API | Accepted as proposed. The version claims in the cell ("default in RN 0.87+", "Node 22.13+", "Kotlin 2.0+") are Spinach's to verify against the pinned versions (W36); HoA does not check them. | frozen | W36
4 | How should the project be structured for a 194-screen app? | Proposal: Feature-based folder structure: /features/spine, /features/plan, /features/vault, /components, /lib, /hooks. Each screen maps to a route for deep-linking and state recovery. | React Native Project Structure (Community) | Accepted. Folder and route names follow the board's section letters (FE-11, FE-15), so a screen ID, a route, a folder and an event name all read the same. | frozen
5 | What is the OTA (Over-The-Air) update strategy? | Proposal: Use EAS Update for JS bundle updates without app store review. Critical bug fixes can be pushed in minutes. Native changes still require store submission. Channel-based releases: production, staging, internal. | Expo EAS Update | Accepted with FE-76's condition. | frozen
6 | What minimum OS versions should be supported? | Proposal: iOS 16+ and Android 10 (API 29)+. This covers ~95% of Indian smartphone users while enabling modern native APIs (Keychain, Keystore, Biometrics). | React Native – Android Version Support · iOS Support | Accepted (FE-20). | frozen

## Navigation & Routing
Table 1
Sr No | Technical Question | Best Practice Proposal | Official Doc Link | Yesly Comments | Status | Board ref | Changed since 26 Sep 2026
1 | Which navigation library should be used? | Proposal: Expo Router (file-based routing) for automatic deep linking, type safety, and deferred bundling. It offers platform-specific look-and-feel and unified mobile/web routing. For a 194-screen app, file-based routing keeps the structure maintainable. | Expo Router Docs | Accepted as proposed (FE-04). | frozen
2 | How should the 194 screens be organized in the router? | Proposal: Route groups: /(spine)/d01 … /(spine)/d13, /(plan)/…, /(vault)/…, /(settings)/…. Each screen ID = one route for deep-linking and state recovery. Use layout files for shared chrome (progress bar, back button). | Expo Router – Layouts | Accepted. Route groups by section letter; one route per screen ID including the letter suffixes (D02a, H01c); the layout files carry the section strip and the progress ring. | frozen | O02
3 | What navigation pattern should be used for the spine flow? | Proposal: Native Stack navigator for the linear spine (D01→D13). Avoid deep nesting of navigators to prevent performance issues. Use a top progress indicator instead of relying on navigation headers. | Expo Router – Stack | Accepted. The top progress indicator is the section strip already drawn on the spine; the relief cards sit between the sections (D12a to D12h). | frozen | D12a
4 | How should deep linking be configured? | Proposal: Universal Links (iOS) and App Links (Android) for <https://yeslyf.com/app/....> Custom scheme yeslyf:// as fallback. Configure app.json with associated domains and intent filters. Handle cold/warm start via Expo Router's built-in linking. | React Native – Linking · Expo Linking | Accepted. Custom scheme yeslyf:// as the fallback, as proposed. to be verified: the domain (W35). | frozen | W35
5 | How should the "return to exact screen after kill/restart" work? | Proposal: Persist current route + scroll position in MMKV on every navigation. On cold start, read last_route and navigate there after auth check. Server-side draft ensures data continuity. | Expo Router – State Restoration | Accepted with one rule: when the device's last route and the server's state disagree, the server wins (FE-37). | frozen | N01
6 | How should modal screens (e.g., Why this matters) be presented? | Proposal: Use presentation: 'modal' in Expo Router for bottom-sheet style modals. Avoid full-screen modals for quick-read content. Lazy-load modal content. | Expo Router – Modals | Accepted. The sheet list is FE-53. | frozen

## Conectivity
Table 1
Sr No | Technical Question | Best Practice Proposal | Doc Link | Yesly Comments | Status | Board ref | Changed since 26 Sep 2026
3 | How should network connectivity be detected? | Proposal: Use @react-native-community/netinfo to detect online/offline transitions. Show a persistent offline banner. Queue writes when offline; auto-sync on reconnect. | NetInfo | Accepted with one rule: only spine and reveal field values queue offline, in encrypted storage, purged on sync. Nothing external (a payment, a consent, an eSign, an order, a booking) ever queues. The offline banner is the one place this is said to the person. | frozen
4 | How should the app behave on low-connectivity (2G/3G)? | Proposal: Reduce image quality, disable auto-play, increase debounce timeouts. Prefetch next 2 spine screens when on Wi-Fi. Show "data saver" toggle in settings. | React Native – Network | Accept the debounce and the prefetch of the next two spine screens. No "data saver" toggle: there is no autoplay to save (A04 and R10 play on tap) and the app is forms and small charts. | frozen | A04, R10

## Performance & Optimization
Table 1
Sr No | Technical Question | Best Practice Proposal | Official Doc Link | Yesly Comments | Status | Board ref | Changed since 26 Sep 2026
1 | What is the performance target for the app? | Proposal: 60 FPS for all animations and list scrolling. TTI < 3s on mid-range Android (e.g., Redmi Note series). Cold start < 2s. JS bundle < 200KB gzipped per route. | React Native – Performance Overview | Accepted as proposed. | frozen
2 | How should the 194 screens be bundled for performance? | Proposal: Lazy-load route groups. Spine screens in one shared chunk (users navigate sequentially). Plan/Vault screens lazy-loaded. Use React.lazy() and Expo Router's deferred bundling. | React Native – Optimizing JavaScript Loading | Accepted as proposed. | frozen
3 | How should long lists (e.g., Vault documents, transaction history) be rendered? | Proposal: Use FlashList (Shopify) or FlatList with getItemLayout. Implement keyExtractor, windowSize, and removeClippedSubviews. Avoid inline anonymous functions in renderItem. | FlashList · FlatList Optimization | FlatList suffices (FE-55). FlashList only if a list grows past a few hundred rows, which none does in V1. | frozen
4 | How should images and assets be handled? | Proposal: Use expo-image for caching, blurhash placeholders, and responsive sizing. Store Vault images in S3; serve via CloudFront with signed URLs. Compress images before upload. | Expo Image | Accepted for assets. Vault images are not V1 (H06 open). The plan PDF goes by email (I10); it is not rendered in the app. | frozen | H06, I10
5 | Should the React Compiler be enabled? | Proposal: Enable React Compiler (experimental) for automatic memoization of components and callbacks, reducing unnecessary re-renders. Test thoroughly before production. | React Compiler | Only the stable release of the React Compiler; not a release candidate on a fixed-date financial app. to be verified: the compiler version Spinach means (W36). | frozen | W36
6 | What Hermes engine configuration should be used? | Proposal: Hermes is the default engine for RN 0.76+. Enable Hermes profiling in dev builds. Use console.log removal in release builds. | Hermes | Accepted as proposed. | frozen

## Security & Authentication
Table 1
Sr No | Technical Question | Best Practice Proposal | Official Doc Link | Yesly Comments | Status | Board ref | Changed since 26 Sep 2026
1 | How should the mobile+OTP authentication flow be implemented? | Proposal: OTP via SMS (Amazon SNS or MSG91). On success, issue short-lived JWT (15 min) + refresh token (7 days, rotated). Store refresh token in React Native Keychain (iOS Keychain / Android Keystore). Never use AsyncStorage for tokens. | React Native – Security · React Native Keychain | The OTP provider is Gupshup (I08, final), WhatsApp OTP as the fallback channel; not Amazon SNS, not MSG91. The verification logic is internal, as I08 says. The token model (a 15-minute JWT, a 7-day rotated refresh token in Keychain or Keystore, never AsyncStorage) is accepted. Rate limits on the board: 5 OTPs per hour (A02), 3 wrong codes (A03); the cooldown and lockout ladder on the Login sheet is accepted on top (JD-LOGIN-W2). | frozen | I08, A02, A03
2 | How should biometric authentication be offered? | Proposal: Use expo-local-authentication for Face ID / Touch ID / Fingerprint. Store a biometric-protected key in Keychain. Offer biometric as a re-auth shortcut after initial OTP login. | Expo Local Authentication | Accepted as proposed (A03 already offers enrolment to a returning user). | frozen | A03
3 | How should PII (PAN, DOB, bank account) be stored on the device? | Proposal: Never store PII in plain storage. Encrypt with MMKV encryption + Keychain-stored key. Clear PII from memory when not in use. Mask PAN in UI (XXXX XXXX 1234). | OWASP MASVS – Storage | Accepted as proposed. PAN masked in the UI; date of birth never stored on the device; nothing in plain storage. | frozen
4 | How should network traffic be secured? | Proposal: TLS 1.3 only. Certificate pinning for API domains. No cleartext traffic (Android usesCleartextTraffic=false). Use react-native-ssl-pinning if needed. | React Native – Security (Network) | Accepted as proposed. | frozen
5 | How should the app handle jailbreak/root detection? | Proposal: Use jail-monkey or react-native-device-info to detect compromised devices. Show a warning and disable sensitive features (AA fetch, payments) on rooted devices. | JailMonkey | Warn on a rooted or jailbroken device; block payments (P04, K04) and execution (E02 to E04, E07 to E11); reading the plan stays allowed. | frozen | P04, K04
6 | What is the session timeout and re-auth policy? | Proposal: 30 min inactivity → re-auth via biometric or password/PIN. | OWASP MASVS – Auth | 30 minutes of inactivity, then biometric if enrolled, otherwise OTP (FE-07). There is no password and no PIN; strike them from the proposal. | frozen

## Native Device Features
Table 1
Sr No | Technical Question | Best Practice Proposal | Official Doc Link | Yesly Comments | Status | Board ref | Changed since 26 Sep 2026
1 | How should push notifications be implemented? | Proposal: Firebase Cloud Messaging (FCM) for Android + APNs for iOS. Use expo-notifications for unified handling. Register FCM token on login; delete on logout. Handle foreground, background, and killed states with a single router. | Expo Notifications | Accepted as proposed (FCM, I12, final). The token is registered on OTP success and deleted on logout and on account deletion (S25). | frozen | I12, S25
2 | How should document upload (CAS PDF, Vault documents) work? | Proposal: Use expo-document-picker for PDF selection. Upload to S3 via presigned URL. Parse CAS PDF server-side (not on device). Show upload progress. Retry on failure. | Expo Document Picker | Accepted: the picker, a presigned upload to S3 (I17), parsing server-side, progress and retry. The parser is I23 (open; W11 closes the CAS source and shares a sample file; owner Product). A10a (waiting for the email) stays as drawn: it waits and reminds; nothing reads an inbox. | frozen | I17, I23, W11, A10a
3 | How should camera/gallery access be handled for Vault uploads? | Proposal: Use expo-image-picker with permission prompts. Compress images to < 1MB before upload. Support HEIC → JPEG conversion. | Expo Image Picker | Not in V1 (FE-46). | frozen
4 | How should contacts access be handled (if needed for referrals)? | Proposal: Use expo-contacts with explicit permission. Hash contact numbers for referral matching (never upload raw contacts). | Expo Contacts | Not in V1. There is no referral feature and no contacts access; nothing about partners or referrals goes in the app. | frozen
5 | How should the app handle background fetch for AA data refresh? | Proposal: Use expo-background-task + expo-task-manager. Schedule periodic AA fetch every 24h (OS-limited). Sync on app foreground as primary mechanism. | Expo Background Fetch | No background fetch on the device. The server fetches against the consent (fetch now plus quarterly for the review; A05, A06); a refresh shows the diff first (A08, Q01). Sync on foreground is a read of state, not a fetch. | frozen | A05, A06, A08, Q01

## CI_CD & Release Management
Table 1
Sr No | Technical Question | Best Practice Proposal | Official Doc Link | Yesly Comments | Status | Board ref | Changed since 26 Sep 2026
1 | What CI/CD pipeline should be used? | Proposal: GitHub Actions for lint → typecheck → unit tests → E2E (Maestro) → EAS Build → EAS Submit. Separate workflows for PR (test only) and main (build + submit). | EAS Build · GitHub Actions | Accepted as proposed. | frozen
2 | How should app signing and provisioning be managed? | Proposal: Use EAS Credentials for managed signing (handles iOS provisioning profiles and Android keystores). Store keystore in EAS, not in repo. | EAS Credentials | Accepted as proposed; the credentials live in HoA's EAS account (FE-73). | frozen | W35
3 | What is the release cadence and channel strategy? | Proposal: Channels: production (App Store/Play Store), staging (TestFlight/Internal Testing), internal (dev builds). OTA updates for JS-only changes; store submission for native changes. | EAS Update – Channels | Accepted as proposed, with FE-76's condition. | frozen
4 | How should versioning be handled? | Proposal: Semantic versioning (major.minor.patch). Build number auto-incremented by EAS. Track OTA update version separately from store version. | EAS Build – Versioning | Accepted as proposed. | frozen
5 | What is the rollback strategy for a bad OTA update? | Proposal: EAS Update supports instant rollback to previous bundle. Keep last 3 stable bundles. Automated rollback on crash rate > 2% within 1 hour. | EAS Update – Rollback | Accepted as proposed. | frozen

## Analytics & Monitoring
Table 1
Sr No | Technical Question | Best Practice Proposal | Official Doc Link | Yesly Comments | Status | Board ref | Changed since 26 Sep 2026
1 | What analytics/event tracking should be implemented in the app? | Proposal: Event taxonomy aligned with wireframe "events" on each screen. Use Segment or a lightweight custom pipeline (Kinesis → S3 → Athena). No PII in event payloads. Batch events; offline queue survives bad network. | Segment RN | Mixpanel over the board's event list (FE-60, FE-61); no Segment and no Kinesis pipeline in V1. Batching and the offline queue are accepted. | frozen | I13, Events
2 | What crash reporting should be used? | Proposal: Sentry for React Native (native crash + JS error tracking). Source maps uploaded during CI. Alert on crash-free sessions < 99.5%. | Sentry React Native | Accepted as proposed (Sentry). | frozen
3 | How should app performance be monitored? | Proposal: Firebase Performance Monitoring for screen render times, network latency, and app start time. Custom traces for plan build and AA fetch. | Firebase Performance | Accepted as proposed; custom traces for the plan build (G01) and the AA fetch (A07). | frozen | G01, A07
4 | How should user feedback be collected? | Proposal: In-app feedback widget (shake-to-report or settings menu). Screenshot + logs attached automatically. Route to Slack/Linear. | Instabug | No Instabug. H07 Help creates a Zoho Desk ticket (I14); Sentry's feedback dialog may ride on a crash report. Nothing routes to Slack or Linear. | frozen | H07, I14

## Integrations (App-Specific)
Table 1
Sr No | Technical Question | Best Practice Proposal | Official Doc Link | Yesly Comments | Status | Board ref | Changed since 26 Sep 2026
1 | How should Account Aggregator (AA) SDK be integrated in React Native? | Proposal: Use a React Native AA SDK (e.g., rn_saafe_aa_sdk or Setu's RN SDK) for redirection to the AA app. Native SDK handles consent flow; app receives callback via deep link. | Sahamati AA Specs | Finvu (I01, final), not Saafe, not Setu. The mode (redirect, webview or SDK) is FE-38 (W37). | frozen | I01, W37
2 | How should CAS PDF upload and parsing work on mobile? | Proposal: User selects PDF via document picker → upload to S3 via presigned URL → parse server-side (not on device). Show parsing progress. Store original in Vault. | Expo Document Picker | Accepted as proposed. The parser is I23 (FE-D2). The original file is filed in the vault (H06) when the vault ships, not in V1. | frozen | I23, H06
3 | Which payment gateway SDK for React Native? | Proposal: Razorpay React Native SDK (India-first). Server-side order creation; SDK handles checkout UI. Webhook verification with signature. Never store card data. | Razorpay RN SDK | Accepted as proposed, with the board's rules: UPI and netbanking only, no cards (brief K1); a recurring UPI mandate for monthly or quarterly (P04; to be verified: mandate type and limits); a single charge for an a la carte call (K04); the webhook is authoritative; the GST split rule is to be verified (P04). | frozen | I09, P04, K04
5 | How should the "guided lookup" for holdings work? | Proposal: Server-side proxy to market data API (NSE/BSE via TrueData). App calls your API, not the market data vendor directly. Cache ISIN → price for 15 min. Fallback to manual entry. | TrueData API | Accord (I05, final), not TrueData. The app calls HoA's backend, never the vendor; the cache TTL is the backend's; the fallback is typing the holding (D02b, D02c). | frozen | I05, D02b, D02c
5 | How should email (Amazon SES) be triggered from the app? | Proposal: App calls your backend API; backend sends email via SES. Never embed SES credentials in the app. Templates managed server-side. | Amazon SES | Accepted as proposed. Templates server-side; the plan PDF and the signed agreement go by email (I10). | frozen | I10

## Open Decisions from Wireframes
Table 1
Sr No | Decision | Wireframe Note | Best Practice Proposal | Yesly Comments | Status | Board ref | Changed since 26 Sep 2026
1 | Client-side storage & session timeout rule | "to be decided by Spinach's data lifecycle map (W21)" | Proposal: No client-side persistence of PII beyond encrypted MMKV cache. Session timeout: 30 min inactivity → biometric or OTP re-auth. Drafts held server-side only. | Accepted as proposed. This row is the data lifecycle map Spinach owes (W21): post it on X00 as agreed and W21 closes. | frozen | W21, X00
2 | Dynamic bands timeline | "shelved until the data flywheel exists" | Proposal: MVP uses fixed bands from M2 tables. Revisit after 10k completed plans. Band choice distributions collected anonymously for future dynamic bands. | Accepted as proposed: fixed bands from the M2 tables in V1; band-choice distributions collected without identity. "After 10k plans" is a suggestion; HoA sets the threshold later. | frozen
3 | Adviser continuity flag | "off by default" | Proposal: Keep off for beta. Enable post-launch if call-centre data supports it. No app change needed (config flag). | Accepted as proposed (K05; the flag is config, off). | frozen | K05
4 | Biometric authentication as default re-auth | Not specified | Proposal: Offer biometric as optional re-auth after first OTP login. Users can disable in settings. Fallback to OTP always available. | Accepted as proposed (A03). | frozen | A03